## 🚀 Mission Control
⚡ HEMISX — CLOUD SCANNER
30-Day Ship-It Plan ¦ Cloud Misconfiguration Scanner MVP
Start Date: March 11, 2026 • Target Ship: April 9, 2026 • 2 Founders, 0 Days Off
PHASE OVERVIEW
Phase | Days | Theme |  | Owner Tasks | Status
WEEK 1 | Days 01–07 | Foundation & Core Engine |  |  | ◯ Not Started
WEEK 2 | Days 08–14 | AWS Checks + AI Risk Scoring |  |  | ◯ Not Started
WEEK 3 | Days 15–21 | Compliance, Reports & UX |  |  | ◯ Not Started
WEEK 4 | Days 22–30 | Beta, Launch & First Revenue |  |  | ◯ Not Started
STATUS LEGEND
☐ To Do |  | Pending task
⚡ In Progress |  | Currently being worked on
✅ Done |  | Completed
🚫 Blocked |  | Needs unblocking
30-DAY TARGETS
🔍 | Scan Coverage |  | IAM · S3 · EC2 · RDS · VPC · Lambda · CloudTrail · SG · KMS
🤖 | AI Risk Scoring |  | Every finding scored by exploitability + blast radius via Claude API
📋 | Compliance Mapping |  | SOC 2 Type II + ISO 27001 control tags on every finding
🛠️ | 1-Click Remediation |  | Auto-generated Terraform / CloudFormation fix suggestions
📊 | Reports |  | Executive PDF + Technical JSON export
🚀 | Live Beta Users |  | 3–5 paying beta customers by Day 30

## 📅 Daily Checklist
⚡ HEMISX — 30-DAY CLOUD SCANNER LAUNCH CHECKLIST
No days off. Ship daily. Every task counts. — Cloud Misconfiguration Scanner MVP
DAY | DATE | PHASE | 👤 FOUNDER — TASK 1 | 👤 FOUNDER — TASK 2 | ✓ | 🤝 CO-FOUNDER — TASK 1 | 🤝 CO-FOUNDER — TASK 2 | ✓ | 🏁 DELIVERABLE | ⚡ PRIORITY
1 | Wed Mar 11 | WEEK 1 Foundation | Audit prototype code — list all working checks & gaps | Set up GitHub monorepo structure (frontend/backend/scanner) | ☐ | Provision AWS dev account, set up IAM roles for scanner access | Deploy base infra: VPC, ECS cluster, RDS (PostgreSQL), Secrets Manager | ☐ | Codebase audit complete, repo structure live | 🔴 CRITICAL
2 | Thu Mar 12 | WEEK 1 Foundation | Design DB schema: findings, resources, scans, users, orgs | Wireframe dashboard: findings list, severity badges, resource tree | ☐ | Build scanner service skeleton (FastAPI) with health endpoint | Implement boto3 AWS session manager — assume-role, multi-account | ☐ | DB schema migrated, scanner skeleton deployed | 🔴 CRITICAL
3 | Fri Mar 13 | WEEK 1 Foundation | Build React app scaffold: auth pages, dashboard shell, routing | Implement JWT auth + Cognito integration on frontend | ☐ | Implement Cognito user pool + JWT middleware on backend | IAM checks module: root account usage, MFA, password policy, old keys | ☐ | Auth flow end-to-end working | 🔴 CRITICAL
4 | Sat Mar 14 | WEEK 1 Foundation | Build findings list UI: filter by severity, service, status | Connect frontend to backend API — display live IAM scan results | ☐ | S3 checks: public ACLs, bucket policy, versioning, encryption, logging | EC2 checks: open SGs (0.0.0.0/0), IMDSv1, public IPs, unencrypted EBS | ☐ | IAM + S3 + EC2 checks returning real findings | 🔴 CRITICAL
5 | Sun Mar 15 | WEEK 1 Foundation | Build finding detail page: resource info, evidence, risk description | Implement severity color coding (Critical/High/Medium/Low/Info) | ☐ | RDS checks: public access, encryption, backup retention, multi-AZ | VPC checks: open NACLs, flow logs disabled, default VPC usage | ☐ | 6 AWS service scanners operational | 🔴 CRITICAL
6 | Mon Mar 16 | WEEK 1 Foundation | Build scan trigger UI: connect AWS account wizard (IAM role ARN input) | Implement onboarding flow: paste ARN → validate → trigger first scan | ☐ | Lambda checks: public function URLs, env var secrets, overpermissive roles | CloudTrail checks: disabled, no log validation, no S3 encryption | ☐ | Onboarding → first scan flow working end-to-end | 🔴 CRITICAL
7 | Tue Mar 17 | WEEK 1 Foundation | Integration test: full scan run on real AWS account, fix all bugs | Week 1 demo recording — internal review, list top 10 issues | ☐ | Security Groups deep-dive checks: port 22/3389/1433/3306 open to world | KMS checks: key rotation disabled, unused keys, overpermissive policies | ☐ | 8 service scanners complete, scan run < 60s | 🔴 CRITICAL
8 | Wed Mar 18 | WEEK 2 AI Engine | Integrate Claude API — build risk scoring prompt with finding context | Display AI risk score + plain-English explanation in finding detail UI | ☐ | Build scan orchestrator: parallel Lambda execution via Step Functions | Implement scan job queue — async scan with status polling | ☐ | AI risk score on every finding with explanation | 🔴 CRITICAL
9 | Thu Mar 19 | WEEK 2 AI Engine | Build natural language query UI — search bar on findings page | NL query: 'Which S3 buckets are publicly accessible?' → filtered results | ☐ | NL query backend: convert NL to filter params via Claude API | Implement finding deduplication — don't re-alert on unchanged findings | ☐ | NL search working on findings | 🟠 HIGH
10 | Fri Mar 20 | WEEK 2 AI Engine | Build resource inventory view: grouped by service, region, account | Add scan history timeline — show finding trends over multiple scans | ☐ | Implement scan scheduling — cron-based continuous scanning (every 6h) | Add CloudWatch Events trigger for scan scheduling | ☐ | Continuous scanning enabled, resource inventory UI done | 🟠 HIGH
11 | Sat Mar 21 | WEEK 2 AI Engine | Build severity dashboard: donut chart (Critical/High/Med/Low counts) | Trend line chart: findings over time (last 30 days) | ☐ | Remediation engine v1: generate Terraform snippet per finding type | Auto-generate CloudFormation fix template for top 10 finding types | ☐ | Remediation snippets generated for all finding types | 🔴 CRITICAL
12 | Sun Mar 22 | WEEK 2 AI Engine | One-click remediation UI: show fix code, copy button, apply button | Implement finding status: Open / Acknowledged / Remediated / Suppressed | ☐ | Remediation apply engine: execute safe fixes via AWS SDK (e.g. enable S3 encryption) | Test auto-remediation in sandbox — validate no destructive actions | ☐ | One-click remediation live for safe fixes | 🔴 CRITICAL
13 | Mon Mar 23 | WEEK 2 AI Engine | Multi-account support UI: add/remove AWS accounts, per-account scan | Account health summary: score per account on dashboard | ☐ | Multi-account scan aggregation: merge findings across all linked accounts | Implement tenant data isolation — per-org DB schema + RLS policies | ☐ | Multi-account scanning working | 🟠 HIGH
14 | Tue Mar 24 | WEEK 2 AI Engine | Week 2 integration test — end-to-end scan on 3 different AWS accounts | Fix top bugs from test, update API docs | ☐ | Performance test: scan 500 AWS resources, target < 60s | Optimize boto3 calls — concurrent API calls with asyncio | ☐ | Scan < 60s for 500 resources confirmed | 🔴 CRITICAL
15 | Wed Mar 25 | WEEK 3 Compliance | Build SOC 2 mapping: tag each finding with Trust Service Criteria control | Build compliance dashboard: SOC 2 coverage % bar chart per control | ☐ | Implement ISO 27001 Annex A control mapping for all findings | Build compliance evidence collector: link findings to controls | ☐ | SOC 2 + ISO 27001 control tags on 100% of findings | 🔴 CRITICAL
16 | Thu Mar 26 | WEEK 3 Compliance | PDF report generator (executive summary): risk score, top findings, trend | Implement PDF styling — branded HemisX report with charts | ☐ | Backend: generate PDF with ReportLab / WeasyPrint, store in S3 | Technical findings JSON/CSV export with full finding metadata | ☐ | Executive PDF report downloadable from dashboard | 🔴 CRITICAL
17 | Fri Mar 27 | WEEK 3 Compliance | Build audit evidence package: ZIP export of all findings + evidence | Map ZIP contents to SOC 2 / ISO 27001 control numbers | ☐ | Implement audit log: all user actions + scan events logged to DB | Audit evidence endpoint: stream ZIP from S3 to browser | ☐ | Audit evidence ZIP download working | 🟠 HIGH
18 | Sat Mar 28 | WEEK 3 Compliance | CI/CD integration: GitHub Actions workflow to scan IaC on PR | Write HemisX GitHub Action (YAML) — PR comment with findings | ☐ | Build IaC scanner: parse Terraform/CloudFormation, flag misconfigs | Webhook endpoint: receive CI/CD scan requests, return findings JSON | ☐ | GitHub Actions integration working on test repo | 🟠 HIGH
19 | Sun Mar 29 | WEEK 3 Compliance | Build Slack integration: alert notifications with finding summary | Slack alert: Critical/High findings → instant notification with link | ☐ | Slack OAuth flow + webhook setup on backend | JIRA integration: auto-create ticket for each Critical finding | ☐ | Slack alerts live, JIRA ticket creation working | 🟡 MEDIUM
20 | Mon Mar 30 | WEEK 3 Compliance | Full UX polish pass: loading states, empty states, error handling | Mobile responsive fixes — test dashboard on mobile, fix layout breaks | ☐ | API hardening: rate limiting, input validation, error sanitization | Write OpenAPI spec for all endpoints — publish to /docs | ☐ | UI polished, API documented | 🟠 HIGH
21 | Tue Mar 31 | WEEK 3 Compliance | Guided onboarding wizard: step-by-step connect AWS → first scan < 15 min | Write onboarding copy, tooltips, help text throughout UI | ☐ | CloudFormation template for IAM role — 1-click deploy for customers | Test onboarding with a friend who doesn't know the product — time it | ☐ | Onboarding < 15 min confirmed by outside tester | 🔴 CRITICAL
22 | Wed Apr 01 | WEEK 4 Launch | Set up Stripe: pricing page, subscription plans, checkout flow | Implement plan gating: Free (1 account, 50 resources) / Pro / Business | ☐ | Stripe webhook handler: provision/deprovision on subscription events | Implement usage metering: track resources scanned per billing period | ☐ | Stripe checkout live, plans enforced | 🔴 CRITICAL
23 | Thu Apr 02 | WEEK 4 Launch | Build landing page: headline, problem/solution, pricing, waitlist CTA | Landing page SEO: meta tags, OG image, sitemap, Google Analytics | ☐ | Set up production environment: separate AWS account, prod RDS, prod ECS | SSL certs, custom domain, CloudFront CDN, WAF rules | ☐ | Landing page live at production domain | 🔴 CRITICAL
24 | Fri Apr 03 | WEEK 4 Launch | Recruit 3–5 beta users from network (SaaS founders, DevOps engineers) | Send personalised beta invites — offer free 90-day Pro access | ☐ | Deploy to production — full smoke test on prod environment | Set up Datadog / CloudWatch monitoring, PagerDuty alerting | ☐ | Prod deployed, monitoring live, first beta user invited | 🔴 CRITICAL
25 | Sat Apr 04 | WEEK 4 Launch | Shadow beta user onboarding — watch them connect AWS, note all friction | Fix top 5 UX issues discovered in beta session 1 | ☐ | Fix all backend errors discovered during beta user's first scan | Add detailed server-side logging for every scan step | ☐ | Beta user 1 fully onboarded, first bugs fixed | 🔴 CRITICAL
26 | Sun Apr 05 | WEEK 4 Launch | Beta feedback session: 30-min call with each beta user | Prioritize feedback — fix critical bugs same day | ☐ | Beta bug bash: address all P0/P1 issues from feedback | Implement beta user requested: email alert for new Critical findings | ☐ | All P0 bugs resolved, email alerts live | 🔴 CRITICAL
27 | Mon Apr 06 | WEEK 4 Launch | Write product launch blog post: 'How HemisX finds AWS misconfigs in 60s' | Prepare Product Hunt launch assets: screenshots, GIF demo, tagline | ☐ | Security hardening: pen test top 10 OWASP on own app, fix any issues | Data backup verification: test RDS snapshot restore procedure | ☐ | Blog post drafted, PH assets ready, security hardened | 🟠 HIGH
28 | Tue Apr 07 | WEEK 4 Launch | Record 3-min product demo video for landing page | Post to Twitter/LinkedIn: 30-day build journey + launch announcement | ☐ | Load test: simulate 50 concurrent scans — fix any bottlenecks | Set up AWS auto-scaling policies for ECS scan workers | ☐ | Demo video live, load test passed | 🟠 HIGH
29 | Wed Apr 08 | WEEK 4 Launch | LAUNCH DAY PREP: final smoke test, all team on standby | Submit to Product Hunt — schedule for 12:01 AM PST | ☐ | Monitor all dashboards: error rates, scan success rate, latency | War room: Slack channel for real-time issue triage during launch | ☐ | Product Hunt submitted, war room active | 🔴 CRITICAL
30 | Thu Apr 09 | WEEK 4 Launch | LAUNCH DAY: respond to every PH comment, DM all beta users for upvotes | Pitch 10 target SMB companies via LinkedIn/email with personalized outreach | ☐ | LAUNCH DAY: monitor infra every 30 min, zero downtime target | Close first paying customer — convert a beta user to paid plan | ☐ | 🚀 PUBLIC LAUNCH — First Paying Customer | 🔴 CRITICAL

## 📊 Sprint Tracker
⚡ HEMISX — SPRINT TRACKER ¦ Cloud Scanner MVP
|  | WEEK 1 Days 1–7 |  | WEEK 2 Days 8–14 |  | WEEK 3 Days 15–21 |  | WEEK 4 Days 22–30
EPIC / FEATURE | DESCRIPTION | F ✓ | CF ✓ | F ✓ | CF ✓ | F ✓ | CF ✓ | F ✓ | CF ✓ | STATUS
🔧 Prototype Cleanup | Audit existing code, restructure monorepo, fill scanner gaps | ☐ | ☐ | — | — | — | — | — | — | Not Started
☁️ AWS Infra Setup | VPC, ECS, RDS, Cognito, IAM roles, Secrets Manager | ☐ | ☐ | — | — | — | — | — | — | Not Started
🔑 Auth & Multi-tenant | Cognito + JWT, org isolation, RBAC roles | ☐ | ☐ | — | — | — | — | — | — | Not Started
🔍 IAM Checks | Root usage, MFA, password policy, access keys, overpermissive | ☐ | ☐ | — | — | — | — | — | — | Not Started
🪣 S3 Checks | Public ACL/policy, encryption, versioning, logging | ☐ | ☐ | — | — | — | — | — | — | Not Started
💻 EC2 Checks | Open SGs, IMDSv1, public IPs, unencrypted EBS volumes | ☐ | ☐ | — | — | — | — | — | — | Not Started
🗄️ RDS Checks | Public access, encryption, backups, multi-AZ | ☐ | ☐ | — | — | — | — | — | — | Not Started
🌐 VPC / SG Checks | Open NACLs, flow logs, default VPC, port 22/3389 open | ☐ | ☐ | — | — | — | — | — | — | Not Started
λ Lambda / CT / KMS | Public URLs, env secrets, CloudTrail disabled, KMS rotation | ☐ | ☐ | — | — | — | — | — | — | Not Started
🤖 AI Risk Scoring | Claude API integration, exploitability scoring, plain-English | — | — | ☐ | ☐ | — | — | — | — | Not Started
🔎 NL Query Interface | Natural language → filter API via Claude | — | — | ☐ | ☐ | — | — | — | — | Not Started
🔄 Continuous Scanning | Scheduler, deduplication, scan history, resource inventory | — | — | ☐ | ☐ | — | — | — | — | Not Started
🛠️ Remediation Engine | Terraform/CF snippets, 1-click safe fixes, status tracking | — | — | ☐ | ☐ | — | — | — | — | Not Started
🏢 Multi-Account | Add/remove AWS accounts, per-account scores, aggregated view | — | — | ☐ | ☐ | — | — | — | — | Not Started
📋 SOC 2 Mapping | Tag findings to Trust Service Criteria controls | — | — | — | — | ☐ | ☐ | — | — | Not Started
📐 ISO 27001 Mapping | Tag findings to Annex A controls | — | — | — | — | ☐ | ☐ | — | — | Not Started
📄 PDF Report | Executive summary PDF, branded, charts, downloadable | — | — | — | — | ☐ | ☐ | — | — | Not Started
📦 Audit Evidence ZIP | Downloadable evidence package mapped to SOC 2 / ISO 27001 | — | — | — | — | ☐ | ☐ | — | — | Not Started
⚙️ CI/CD Integration | GitHub Actions scan on PR, webhook endpoint, IaC scanner | — | — | — | — | ☐ | ☐ | — | — | Not Started
🔔 Slack / JIRA Alerts | Real-time Slack notifications, auto-JIRA ticket creation | — | — | — | — | ☐ | ☐ | — | — | Not Started
🎯 Onboarding Wizard | < 15 min connect AWS → first scan, CF template for IAM role | — | — | — | — | ☐ | ☐ | — | — | Not Started
💳 Stripe Billing | Plans, checkout, webhooks, usage metering, plan gating | — | — | — | — | — | — | ☐ | ☐ | Not Started
🌍 Landing Page | Headline, pricing, demo video, PH-ready assets | — | — | — | — | — | — | ☐ | ☐ | Not Started
🚀 Production Deploy | Prod AWS env, CloudFront, WAF, SSL, Datadog monitoring | — | — | — | — | — | — | ☐ | ☐ | Not Started
👥 Beta Program | 3–5 beta users, onboarding calls, feedback loop, bug fixes | — | — | — | — | — | — | ☐ | ☐ | Not Started
🔐 Security Hardening | OWASP top 10 self-pentest, rate limiting, backup verification | — | — | — | — | — | — | ☐ | ☐ | Not Started
📣 Launch | Product Hunt, blog post, social posts, first paying customer | — | — | — | — | — | — | ☐ | ☐ | Not Started

## 📈 Launch Metrics
⚡ HEMISX — LAUNCH METRICS TRACKER
PRODUCT | METRIC | TARGET | ACTUAL | STATUS
Scanner | Scan completion time | < 60 seconds
Scanner | AWS services covered | 9 services
Scanner | Finding types implemented | 40+ check types
AI Layer | Risk score accuracy (QA) | Validated on 20 findings
AI Layer | NL query response time | < 3 seconds
Compliance | SOC 2 controls mapped | 100% coverage
Compliance | ISO 27001 controls mapped | 100% coverage
Onboarding | Time to first scan | < 15 minutes
Performance | Dashboard load time | < 2 seconds P95
Performance | Uptime (prod) | 99.9%
Beta | Beta users onboarded | 3–5 users
Beta | Beta NPS score | >= 8/10
Revenue | Paying customers by Day 30 | 1+ customer
Revenue | MRR by Day 30 | $500+
Marketing | Product Hunt upvotes | Top 5 of day
Marketing | Landing page signups | 50+ signups